## Risk Register
# | Risk Category | Identified Risk | Date Identified | Likelihood (Initial) | Consequence (Initial) | Score | Control/Mitigant | Likelihood (New) | Consequence (New) | New Score | Owner | Last Review | Initial Risk Light | Final Risk Light | Traffic Light | Scheduled | Initial Risk Score | Final Risk Score | Risk Score | Risk Level | Present | Priority
1 | Strategic | ISO 9001 | 2016-11-01 | 3 | 5 | High | Desin and certify all branches by 30/6/17. Managed through quality objectives | 5 | 2 | Moderate | Ray McMurrich | 2016-12-01 | RED | AMBER | AMBER | 2017-06-30 | 15 | 10 | 10 | Moderate | TRUE
2 | Compliance | Compliance to relevant Statutory and Regulatory requirements for chairs | 2016-11-01 | 2 | 1 | Low | No regulations or codes concerning chairs | 1 | 1 | Low | Ray McMurrich | 2016-12-01 | GREEN | GREEN | GREEN | 2017-06-30 | 2 | 1 | 1 | Low | TRUE
3 | Operational | Interested parties | 2016-11-01 | 5 | 2 | Moderate | Ensure interested parties register is reviewed at each management review and impement objectives and operational as needed. | 5 | 1 | Low | Ray McMurrich | 2016-12-01 | AMBER | GREEN | GREEN | 2017-06-30 | 10 | 5 | 5 | Low | TRUE
4 | Compliance | Compliance to relevant Statutory and Regulatory requirements for WHS | 2016-10-01 | 5 | 4 | High | WHS program | 3 | 3 | Moderate | Ray McMurrich | 2016-12-01 | RED | AMBER | AMBER | 2017-06-30 | 20 | 9 | 9 | Moderate | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
End | [20 empty] | FALSE
Formulas:
Scheduled = IF([Last Review]<>"",EOMONTH([Last Review],ReviewFreq),"")
Scheduled = IF([Last Review]<>"",EOMONTH([Last Review],6),"")

## Risk Stats
Risk Stats
Traffic Lights
At 11-Oct-2024
Green | 2
Amber | 2
Red | 0
Total | 4
Final Risk Assessment
Initial Risk | Red | Amber | Green | None | Total
Red | 0 | 2 | 0 | 0 | 2
Amber | 0 | 0 | 1 | 0 | 1
Green | 0 | 0 | 1 | 0 | 1
Total | 0 | 2 | 2 | 0 | 4

## RiskMatrix
|  |  | 2 | 3 | 4 | 5 | 6
Risk Likelihood
|  |  | 1 - Very Low | 2 - Low | 3 - Moderate | 4 - High | 5 - Very High
5 | Risk Consequences | 5 - Very High | 5 | 10 | 15 | 20 | 25
4 |  | 4 - High | 4 | 8 | 12 | 16 | 20
3 |  | 3 - Moderate | 3 | 6 | 9 | 12 | 15
2 |  | 2 - Low | 2 | 4 | 6 | 8 | 10
1 |  | 1 - Very Low | 1 | 2 | 3 | 4 | 5
|  |  | 1 to 5 | 6 to 11 | 12 to 25
|  | Assessment & Action | Low (None) | Moderate (Possibly) | High (Definitely)

## Definition Tables
RIO Categories (add to as required) | RISK Categories (add to as required) |  | Risk Likelihod |  |  |  |  | Risk Review Frequency (Default) | 6
SOURCE | Business Risk Category | Decription | Likelihood | Rating | Like-Desc
Document Management | Strategic | Decisions Concerning Your Business’ Objectives | None | 0 | 0 - None
External Audit | Compliance | The Need To Comply With Laws, Regulations, Standards And Codes Of Practice | Very Low | 1 | 1 - Very Low
Internal Audit | Financial | Financial Transactions, Systems And Structure Of Your Business | Low | 2 | 2 - Low
Management Review | Operational | Your Operational And Administrative Procedures | Moderate | 3 | 3 - Moderate
Observations | Environmental | External Events That The Business Has Little Control Over Such Unfavourable Weather Or Economic Co | High | 4 | 4 - High
Preventive Action | Reputational | The Character Or Goodwill Of The Business | Very High | 5 | 5 - Very High
Risk
Improvement
Opportunity
Risk Consequence
|  |  | Consequence | Rating | Cons-Desc
|  |  | Very Low | 1 | 1 - Very Low
|  |  | Low | 2 | 2 - Low
|  |  | Moderate | 3 | 3 - Moderate
|  |  | High | 4 | 4 - High
|  |  | Very High | 5 | 5 - Very High
Risk Score
|  |  | DESCRIPTION | Escalation | Risk-Desc | FROM | TO | RIO Level
|  |  | None | None | 0 to 0 | 0 | 0 | None (None)
|  |  | Low | None | 1 to 5 | 1 | 5 | Low (None)
|  |  | Moderate | Possibly | 6 to 11 | 6 | 11 | Moderate (Possibly)
|  |  | High | Definitely | 12 to 25 | 12 | 25 | High (Definitely)