## RIO Register
No. | Source | Details | Raised | Originator | Reviews, Controls, Root cause, Actions | Risk Likelihood | Risk Consequence | Risk Assesment (Escalation) | Target | Who | Review of effectiveness | Completed | Approved | Changes | Traffic Light | Scheduled | Risk Score | Present
1 | Example | IQA Purchasing Vehicles | 2016-02-26 | John Mason | Amend procedure and re-issue. | 2 | 4 | Moderate (Consider) | 2016-05-01 | John Mason |  |  |  | 2 | BLUE | 2016-05-31 | 8 | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
End
Formulas:
Traffic Light = IF(OR(AND([Raised]<>"",[Completed]="",[Target]<TODAY()),AND([Raised]<>"",[Target]="")),"BLUE",IF([Changes]+1>4,"Red",CHOOSE([Changes]+1,"","Green","Amber","Red")))
Scheduled = IF([Target]="","",EOMONTH([Target],0))

## RIO Stats
Next Mgt Review | 2016-11-30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
From | 2015-12-01
To | 2016-11-30
| TOTAL | DOCUMENT MANAGEMENT | EXTERNAL AUDIT | INTERNAL AUDIT | MANAGEMENT REVIEW | OBSERVATIONS | PREVENTIVE ACTION | RISK | IMPROVEMENT | OPPORTUNITY | EXAMPLE |  |  |  |  | RISK LIKELIHOD
Open | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Raised | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | 0
Closed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Open at end | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | 0
Escalated to RR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Last 5 Years
From | 1/1/2020 | 1: 1/1/2021; 2: 1/1/2022; 3: 1/1/2023; 4: 1/1/2024; 6: 2024-10-01; 7: 2024-10-31
To | 2020-12-31 | 1: 2021-12-31; 2: 2022-12-31; 3: 2023-12-31; 4: 2024-12-31; 9: October 2024; 10: Column1
Open | 1 | 1: 1; 2: 1; 3: 1; 4: 1; 9: Open; 10: 1
Raised | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 9: Raised; 10: 0
Closed | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 9: Closed; 10: 0
Open at end | 1 | 1: 1; 2: 1; 3: 1; 4: 1; 9: Open at end; 10: 1
Escalated to RR | 0 | 1: 0; 2: 0; 3: 0; 4: 0; 9: Escalated to RR; 10: 0
[10 empty] | Traffic Lights | Column1
At 16-Oct-2024
[10 empty] | Blue | 1
[10 empty] | Green | 0
[10 empty] | Amber | 0
[10 empty] | Red | 0
[10 empty] | Escalated to RR | 0

## RiskMatrix
|  |  | 2 | 3 | 4 | 5 | 6
Risk Likelihood
|  |  | 1 - Very Low | 2 - Low | 3 - Moderate | 4 - High | 5 - Very High
5 | Risk Consequences | 5 - Very High | 5 | 10 | 15 | 20 | 25
4 |  | 4 - High | 4 | 8 | 12 | 16 | 20
3 |  | 3 - Moderate | 3 | 6 | 9 | 12 | 15
2 |  | 2 - Low | 2 | 4 | 6 | 8 | 10
1 |  | 1 - Very Low | 1 | 2 | 3 | 4 | 5
|  |  | 1 to 5 | 6 to 11 | 12 to 25
|  | Assessment & Escalation | Low (None) | Moderate (Consider) | High (Definitely)

## Definition Tables
RIO Categories (add to as required) |  |  |  |  | RISK Categories (add to as required)
SOURCE |  |  |  |  | Business Risk Category | Decription
Document Management |  |  |  |  | Strategic | Decisions Concerning Your Business’ Objectives
External Audit |  |  |  |  | Compliance | The Need To Comply With Laws, Regulations, Standards And Codes Of Practice
Internal Audit |  |  |  |  | Financial | Financial Transactions, Systems And Structure Of Your Business
Management Review |  |  |  |  | Operational | Your Operational And Administrative Procedures
Observations |  |  |  |  | Environmental | External Events That The Business Has Little Control Over Such Unfavourable Weather Or Economic Co
Preventive Action |  |  |  |  | Reputational | The Character Or Goodwill Of The Business
Risk
Improvement
Opportunity
Example
Risk Likelihod |  |  |  |  | Worksheet Header (Enter values here if you want a specific header)
Likelihood | Rating | Like-Desc |  |  | Worksheet | Header Title
None | 0 | 0 - None |  |  | RIO Register | Risks, Improvements, Opportunities Register
Very Low | 1 | 1 - Very Low |  |  | RIO Stats | ISO9001 Risks, Improvements, Opportunities October 2024
Low | 2 | 2 - Low |  |  | RiskMatrix | Risk Matrix
Moderate | 3 | 3 - Moderate
High | 4 | 4 - High
Very High | 5 | 5 - Very High
Risk Consequence
Consequence | Rating | Cons-Desc
Very Low | 1 | 1 - Very Low
Low | 2 | 2 - Low
Moderate | 3 | 3 - Moderate
High | 4 | 4 - High
Very High | 5 | 5 - Very High
Risk Score
DESCRIPTION | Escalation | Risk-Desc | FROM | TO | RIO Level
None | None | 0 to 0 | 0 | 0 | None
Low | None | 1 to 5 | 1 | 5 | Low (None)
Moderate | Consider | 6 to 11 | 6 | 11 | Moderate (Consider)
High | Definitely | 12 to 25 | 12 | 25 | High (Definitely)
Risk Review Frequency (Default) | 6

## HELP!!!!
How to use this register - Some basic HELP
This register is used to record Risks, Improvements and Opportunities (RIOs), and produce some basic statistics.
It has a couple of macros in it so macros should be enabled in Excel
When an entry is made in Source, the next number is automatically populated (it’s the first of the macros). It's the number of the cell above plus one
The values that can be entered in "Source" are restricted to the values in a table in column A of the worksheet "Definition Tables". These can be added to, modified or deleted.
Details, Raised, Originator and Reviews/Controls/Root cause/Actions are straightforward
In Risk Likelihood enter a number representing the likelihood of the risk occurring from 1 (very low) to 5 (very high)
In Risk Consequence enter a number representing the consequemce of the risk occurs from 1 (very low) to 5 (very high)
Risk Assesment (Escalation) is calculated based on the table "Risk Score" in worksheet Definition Tables
Target, Who, Review of effectiveness, Completed and Approved are hopefully straighforward
Changes, Traffic Light, Scheduled, Risk Score, Present are all calculated columns
Changes reflects the number of changes made to the target date and drives the colour of the "Target Date" cell (the number of changes can be adjusted manually if ncessary)
Traffic Light - Blue if Target date is this month, Green if # changes = 1, Amber if # changes = 2, Red if # changes >2
Printing
Another macro runs whenever the workbook is saved and will adjust the footer of each page to display the date the Workbook was last saved.
If you want to change the description in the header for a sheet, enter the required value in the table in Definition Tables M2:N10
RIO Stats
These are some basic summaries of the number of RIOs in the period. The first table is intended for presentation at Management Reviews and by default are for the 12 months preceeding the next Management Review (which is entered in cell C1). It shows the number of RIOs Open, Raised, Closed, Open at end and Escalated to Risk Register for the period by the "source" type (as defined in the table in column A of Definition Tables.
The second table shows the number of RIOs Open, Raised, Closed, Open at end and Escalated to Risk Register for the previous 5 calendar years
And finally the number of RIOs Open, Raised, Closed, Open at end and Escalated to Risk Register as at today's date and the number of RIOs for each Traffic Light